## MOM
Date | S.no | Task Discussion | Responsible | Pending Activities(Task from previous meeting) | For Next Meeting
2021-04-02 | 1 | Domain POOL selection | ALL | NA | Will look into the Algorithms Basics which are suitable for the domain of the Problem.
Recommendation : Amazon retail
Games : Quick Draw
Medical : Cancer detetction
Detection: IDS, Anomaly , Spotify, Fraud, Email & Spamming
| 2 | Algorithm Pool : Selection
GA/GP
ML : Ensemble
ANN
Auto ML
| 3 | Detection as finalized Domain
2021-04-05 | 1 | Domain - Music Genre Classification | ALL | Completed-->Looked into the various algortihms and datasets suitable to start the further activities. | 1. Will look into the implementation details for each algorithms. 2. Look into the dataset and modelling part . 3.Will discuss the caveats in next meeting.
| 2 | Data set finalization(GTZan)
| 3 | Algorithm Finalization
XGBoost
ResNet/VGG-16
KNN,SVM + GA
2021-04-10 | 1 | Domain - Music Genre Classification - finalized | XGBoost - Sneha RNN-LSTM - Vivek/Salil GA+KNN/SVM - Priyanka | 1.Issue with CNN- shouldn't use transfer learning techniques. | 1. Divided the task for individuals who is taking up which algorithm to implement. 2. Will work on Optimization and Hyperparameter tuning once done with implementation.
| 2 | Data set finalization(GTZan) - Finalized
| 3 | Algorithm Finalization - LSTM is still under discussion
XGBoost
RNN-LSTM
KNN,SVM + GA
2021-04-16 | 1 | Algorithm Finalization - All 3 finalized | XGBoost - Sneha/Vivek RNN-LSTM - Priyanka/Salil GA+SVM -Vivek Sneha | Parameters to compare the perfromance of Algo | 1. Finish coding part 2. Optimization and Hyperparameter tuning. 3. Report Writing to be started
| 2 | Implementation of algorithms
| 3 | Parameters identification for comparing algorithms:
Accuracy , Precision/Sensitivity , Execution Time and
other to brainstrom,
| 4 | Report format discussion
2021-04-25 | 1 | Implementation of algorithms - Finsihed | Optimization/Hyperperamater Tuning - Vivek/Priyanka Research Papers -All Report Writing - Salil/Sneha PPt - Priyanka to start with | Points to be covered for report writing. | 1. Finish implementation and optimization by 27th 1st half. 2.Finish Report Writing 3. Presentation Slides 4. Recording and submission by 28th April.
| 2 | Hyperparameter tuning/Optimization - In process
| 3 | Research papers - Finalized
| 4 | Report Writing - Inprocess
| 5 | Presentation Slides