## MOM
Date | S.no | Task Discussion | Responsible | Pending Activities(Task from previous meeting) | For Next Meeting
2021-04-02 | 1 | Domain POOL selection | ALL | NA | Will look into the Algorithms Basics which are suitable for the domain of the Problem.
Recommendation : Amazon retail
Games : Quick Draw
Medical : Cancer detetction
Detection: IDS, Anomaly , Spotify, Fraud, Email & Spamming
| 2 | Algorithm Pool : Selection
GA/GP
ML : Ensemble
ANN
Auto ML
| 3 | Detection as finalized Domain
2021-04-05 | 1 | Domain - Music Genre Classification | ALL | Completed-->Looked into the various algortihms and datasets suitable to start the further activities. | 1. Will look into the implementation details for each algorithms. 2. Look into the dataset and modelling part . 3.Will discuss the caveats in next meeting.
| 2 | Data set finalization(GTZan)
| 3 | Algorithm Finalization
XGBoost
ResNet/VGG-16
KNN,SVM + GA
2021-04-10 | 1 | Domain - Music Genre Classification | XGBoost - Sneha RNN-LSTM - Vivek/Salil GA+KNN/SVM - Priyanka | 1.Issue with CNN- shouldn't use transfer learning techniques. | 1. Divided the task for individuals who is taking up which algorithm to implement. 2. Will work on Optimization and Hyperparameter tuning once done with implementation.
| 2 | Data set finalization(GTZan)
| 3 | Algorithm Finalization
XGBoost
RNN-LSTM
KNN,SVM + GA